2026 TURNAROUND MECHANICAL DECOKE

Coker Furnace — PR-170002

Job Report  |  USADebusk  |  Cenovus Lima Refinery — Lima, OH

| PROJECT NO. | FACILITY | EXECUTION | PROJECT MANAGER |
| --- | --- | --- | --- |
| USA26046 | Cenovus Lima Refinery | Sep 27 – 30, 2026 | Peter Campbell |
| WORK ORDER | SCOPE | HEATER | DURATION |
| 82096135 | TA Mechanical Decoke | PR-170002 | 4 days |

| 73 | 0 | 64 | 4 |
| --- | --- | --- | --- |
| OPERATING HOURS | STAND-BY HOURS | PIGS RUN | PASSES |

Project Information

Customer Details

| FACILITY | Cenovus Lima Refinery |
| --- | --- |
| ADDRESS | 1150 S Metcalf St, Lima, OH 45804 |
| WORK ORDER | 82096135 |
| CONTACT | Kaleb Dodson |

Project Details

| SCOPE | 2026 turnaround mechanical decoke of the Coker Furnace |
| --- | --- |
| EXECUTION | September 27 – 30, 2026 (4 days) |
| HEATER | PR-170002 Coker Furnace |
| EQUIPMENT | (1) Trimax Pumper (Trimax 5) · (1) Support Unit · 4x3 Pump · Crew Truck |

Crew Details

| PROJECT MANAGER | Peter Campbell |
| --- | --- |
| SHIFT LEAD | Day — Peter Campbell, Jesse Utsey (Sep 30); Night — James McDaniel |
| DAYSHIFT | Marshall Douglas, Travis Trenholm, Adrian Garza, David Charles, Blake Harman |
| NIGHTSHIFT | Mikee Green, Justin Kelly, Jeremiah Harman |

Project Duration

| SCOPE | UNIT | RIG | PIG | SMART PIG | SUBTOTAL |
| --- | --- | --- | --- | --- | --- |
| PR-170002 Coker Furnace | Trimax 5 | 22 | 51 | 0 | 73 |

Stand-By Summary

No stand-by was recorded on the daily service receipts: all 73 pumping-unit hours on this heater were operating hours.

PR-170002 — Coker Furnace

| Number of Passes | 4, pigged as 3 circuits: convection (4 coils looped as one), radiant A + B, radiant C + D |
| --- | --- |
| Total Footage | 15,904 ft (3,976 ft per pass) |
| Tube ID | 3.398" (4" OD tube); radiant outlet section 3.624" (4" Sch 120) |
| Metallurgy | 9Cr-1Mo |
| Return Bends | Cast 180° U-bends |

Decoking Analysis:  The convection section showed light fouling and the radiant section moderate fouling. The crossovers were removed, the convection was pigged as a single circuit, and the radiant passes were looped A + B and C + D with temporary 180° returns at the radiant inlet flanges. Average pigging time was approximately 51 hours per circuit.

PR-170002 - task hours by shift, from the daily service receipts.

Pigs Used

| SIZE — QTY | SIZE — QTY | SIZE — QTY | SIZE — QTY | SIZE — QTY |
| --- | --- | --- | --- | --- |
| 3" — 3 | 3.25" — 6 | 3.5" — 6 | 3.75" — 14 | 4" — 2 |
| 3.125" — 3 | 3.375" — 5 | 3.625" — 21 | 3.875" — 4 |  |
| TOTAL — 64 |  |  |  |  |

Flow Tests

| All convection GPM; BEFORE PSI; AFTER PSI; Δ PSI. 350; 435; 375; 60. 300; 330; 290; 40. 250; 220; 180; 40. | Passes A + B GPM; BEFORE PSI; AFTER PSI; Δ PSI. 350; 370; 275; 95. 300; 290; 200; 90. 250; 210; 146; 64. | Passes C + D GPM; BEFORE PSI; AFTER PSI; Δ PSI. 350; 419; 287; 132. 300; 320; 219; 101. 250; 225; 159; 66. |
| --- | --- | --- |

Project Summary

USADebusk performed the mechanical decoke of the Coker Furnace (PR-170002) for Cenovus at the Lima Refinery during the 2026 turnaround, September 27 – 30, on Trimax 5. The crossovers were removed and the heater was pigged as three circuits: the convection as one, and the radiant passes looped A + B and C + D. The heater ran 73 operating hours with no stand-by, using 64 pigs.

Project Close

The Coker Furnace was cleaned and returned to Cenovus, and all equipment was demobilized from the facility on September 30, 2026.

USADebusk thanks the Cenovus Lima team for their coordination and support throughout the turnaround, and we look forward to continuing to serve your decoking and pigging needs.

Jesse Utsey  |  Project Manager, USADebusk

713-252-8516  |  JUtsey@USADebusk.com