## Inputs
USA26046 Cenovus Lima — Vac Charge Furnace (PR-170029) change-order inputs
Blue = input. Yellow = needs Cory's call before submission.
Input | Value | Source
Equipment rate ($/hr) | 800 | Cory Walker 2026-10-12: $19,200 per 24 hrs / 24
Personnel rate ($/hr) | 210.42 | Cory Walker 2026-10-12: $2,525 per 12-hr shift / 12, rounded
Per diem ($/shift) | 450 | Cory Walker 2026-10-12
Hours per shift | 12 | Standard 12-hr shift
Quoted hours for per-diem basis | 110 | Cory Walker 2026-10-12 ('quoted 110 hours or 9.166 shifts'). DSP26013 quotes the Vac at 134 hrs — confirm which
Alt. stand-by equipment rate ($/hr) | 700 | DSP26013 rate sheet: pumper stand-by $400 + support $30 + press $245 + truck $25
Combined hourly ($/hr) | 1010.42 | Equipment + personnel

## Stand-by Detail
Vac stand-by by service receipt (all booked as plant down time)
Receipt | Shift | Stand-by hrs | Cause (from the receipt)
7077 | Night 2026-09-19 | 7 | Plant down time waiting on Trimax 6 to be spotted in the unit (spotted 18:00)
7078 | Day 2026-09-20 | 12 | 12" radiant-outlet launchers not yet installed by plant
7079 | Night 2026-09-20 | 10 | 12" radiant-outlet launchers still outstanding
7080 | Day 2026-09-21 | 12 | Waiting for fitters to install the 12" launchers
7081 | Night 2026-09-21 | 8 | Waiting on the same 12" launchers (installed 02:00)
7091 | Night 2026-09-26 | 3 | Waiting for fitters to move the 12" launchers to passes 5, 7, 8
Total |  | 52 | Source: PR-170029 Field Notes, receipts 7077-7081, 7091

## Vac Change Orders
Vac Charge Furnace (PR-170029) — change orders and quote comparison
Task | Quoted hrs | Actual hrs | Variance hrs
Rig-in | 6 | 14 | 8 | Quoted: DSP26013 Vac line (134 hrs). Actual: receipts 7077-7100, PR-170029 Final Hours.
Pig (decoke) | 66 | 63 | -3
Smart pig | 38 | 74 | 36
Rig-over | 18 | 8 | -10
Rig-out | 6 | 36.5 | 30.5
Stand-by | 0 | 52 | 52
Total | 134 | 247.5 | 113.5
Line | Hours | Equipment | Personnel | Per diem | Total
CO-1 Stand-by (plant-caused) | 52 | 41600 | 10941.84 | 1950 | 54491.84 | Per diem allocated by the CO's own hours (hrs / 12 x $450)
CO-2 Smart pigging over quote | 36 | 28800 | 7575.12 | 1350 | 37725.12
Change orders total | 88 | 70400 | 18516.96 | 3300 | 92216.96
Decoking time saved vs quote | Hours | Equipment | Personnel | Per diem | Total
Pig (decoke) under quote | 3 | 2400 | 631.26 | 112.5 | 3143.76
Rig-over under quote | 10 | 8000 | 2104.2 | 375 | 10479.2
Savings total | 13 | 10400 | 2735.46 | 487.5 | 13622.96
Not covered by either CO | Hours | Equipment | Personnel | Per diem | Total
Rig-in + rig-out over quote | 38.5 | 30800 | 8101.17 | 1443.75 | 40344.92 | Inlet-piping/launcher delays and both filter presses cleaned at rig-out. Decide: price it, or leave it out.
Checks and alternatives | Value
Productive hrs reconcile (quote + COs + uncovered − savings) | 195.5 | OK = actual productive
CO-1 equipment at rate-sheet stand-by ($700/hr) | 36400 | 5200 | difference vs $800 basis
Per diem over quote, whole job (Cory's basis) | 5156.25 | Basis: (247.5 shift hrs − quoted hrs) / 12 x $450; use instead of the per-CO per diem, not as well as

## Crude Smart Pig
Crude Furnace (PR-170028) — quoted vs actual, smart pig breakout
Task | Quoted hrs | Actual hrs | Variance hrs
Rig-in | 6 | 12 | 6
Pig (decoke) | 90 | 118 | 28
Smart pig | 15 | 38.25 | 23.25
Rig-over | 20 | 11.75 | -8.25
Rig-out | 6 | 12 | 6
Stand-by | 0 | 0 | 0
Total | 137 | 192 | 55
Line | Hours | Equipment | Personnel | Per diem | Total
Smart pigging over quote | 23.25 | 18600 | 4892.265 | 871.875 | 24364.14
Source: PR-170028 Task Durations (re-split by the receipt summaries' clock times). No receipt records stand-by or a delayed start on the Crude. No smart-pig vendor is named; third-party services written 0.