2026 TURNAROUND MECHANICAL DECOKE

Crude Furnace — PR-170028

Job Report  |  USADebusk  |  Cenovus Lima Refinery — Lima, OH

| PROJECT NO. | FACILITY | EXECUTION | PROJECT MANAGER |
| --- | --- | --- | --- |
| USA26046 | Cenovus Lima Refinery | Sep 17 – 25, 2026 | Peter Campbell |
| WORK ORDER | SCOPE | HEATER | DURATION |
| 82036534 | TA Mechanical Decoke | PR-170028 | 9 days |

| 192 | 0 | 201 | 8 |
| --- | --- | --- | --- |
| OPERATING HOURS | STAND-BY HOURS | PIGS RUN | PASSES |

Project Information

Customer Details

| FACILITY | Cenovus Lima Refinery |
| --- | --- |
| ADDRESS | 1150 S Metcalf St, Lima, OH 45804 |
| WORK ORDER | 82036534 |
| CONTACT | Alfredo Trevino |

Project Details

| SCOPE | 2026 turnaround mechanical decoke of the Crude Furnace, with filtration and smart-pig support |
| --- | --- |
| EXECUTION | September 17 – 25, 2026 (9 days) |
| HEATER | PR-170028 Crude Furnace |
| EQUIPMENT | (1) Trimax Pumper (Trimax 5) · (1) Support Unit · (1) Filter Press (Press 3) · Crew Truck |

Crew Details

| PROJECT MANAGER | Peter Campbell |
| --- | --- |
| SHIFT LEAD | Day — Peter Campbell; Night — James McDaniel |
| DAYSHIFT | Rodney Lynch, Brody Lebleau, David Charles, Adrian Garza, Travis Trenholm |
| NIGHTSHIFT | Justin Kelly, Mikee Green, Jeremiah Harman |

Project Duration

| SCOPE | UNIT | RIG | PIG | SMART PIG | SUBTOTAL |
| --- | --- | --- | --- | --- | --- |
| PR-170028 Crude Furnace | Trimax 5 | 35.75 | 118 | 38.25 | 192 |

Stand-By Summary

No stand-by was recorded on the daily service receipts: all 192 pumping-unit hours on this heater were operating hours.

PR-170028 — Crude Furnace

| Number of Passes | 8, pigged individually |
| --- | --- |
| Total Footage | 23,856 ft (2,982 ft per pass) |
| Convection Tube ID | 5.761" (6" Sch 80S) |
| Radiant Tube ID | 7.625" (8" Sch 80S) |
| Metallurgy | A312 TP317/317L |
| Return Bends | 180° short-radius |
| Smart Pigging | Yes — Intero |

Decoking Analysis:  Fouling was concentrated in the upper 8" radiant tubes, tubes 1 through 5, with lighter fouling through the balance of the coil. Average pigging time was approximately 39 hours per pass.

PR-170028 - task hours by shift, from the daily service receipts.

Pigs Used

| SIZE — QTY | SIZE — QTY | SIZE — QTY | SIZE — QTY |
| --- | --- | --- | --- |
| 6" — 30 | 6.25" — 50 | 8" — 40 | 8.5" — 12 |
| 6.125" — 12 | 7.75" — 3 | 8.25" — 54 |  |
| TOTAL — 201 |  |  |  |

Flow Tests

| Pass 1 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 750; 310; 270; 40. 700; 285; 255; 30. 650; 250; 225; 25. | Pass 2 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 750; 315; 280; 35. 700; 295; 270; 25. 650; 270; 255; 15. |
| --- | --- |

| Pass 3 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 750; 350; 305; 45. 650; 275; 220; 55. 550; 220; 165; 55. | Pass 4 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 750; 324; 295; 29. 650; 248; 230; 18. 550; 177; 165; 12. |
| --- | --- |

| Pass 5 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 750; 270; 245; 25. 650; 215; 190; 25. 550; 155; 125; 30. | Pass 6 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 800; 300; 285; 15. 700; 280; 255; 25. 600; 240; 205; 35. |
| --- | --- |

| Pass 7 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 800; 290; 265; 25. 700; 265; 240; 25. 600; 230; 205; 25. | Pass 8 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 800; 250; 221; 29. 700; 220; 190; 30. 600; 200; 165; 35. |
| --- | --- |

Project Summary

USADebusk performed the mechanical decoke of the Crude Furnace (PR-170028) for Cenovus at the Lima Refinery during the 2026 turnaround, September 17 – 25, on Trimax 5 with filtration through Press 3. The eight passes were run in three sets — 8, 7 and 6; then 5, 4 and 3; then 1 and 2 — and smart-pigged by Intero after cleaning. The heater ran 192 operating hours with no stand-by, using 201 pigs.

Project Close

The Crude Furnace was cleaned, rigged out and returned to Cenovus on September 25, 2026.

USADebusk thanks the Cenovus Lima team for their coordination and support throughout the turnaround, and we look forward to continuing to serve your decoking and pigging needs.

Peter Campbell  |  Pigging and Decoking SME

Cell: 832-920-4253  |  pcampbell@usadebusk.com