2026 TURNAROUND MECHANICAL DECOKE

HDS Furnace — PR-175169

Job Report  |  USADebusk  |  Cenovus Lima Refinery — Lima, OH

| PROJECT NO. | FACILITY | EXECUTION | PROJECT MANAGER |
| --- | --- | --- | --- |
| USA26046 | Cenovus Lima Refinery | Sep 25 – 27, 2026 | Peter Campbell |
| WORK ORDER | SCOPE | HEATER | DURATION |
| — | TA Mechanical Decoke | PR-175169 | 3 days |

| 41 | 2 | 16 | 4 |
| --- | --- | --- | --- |
| OPERATING HOURS | STAND-BY HOURS | PIGS RUN | PASSES |

Project Information

Customer Details

| FACILITY | Cenovus Lima Refinery |
| --- | --- |
| ADDRESS | 1150 S Metcalf St, Lima, OH 45804 |
| CONTACT | Alfredo Trevino |

Project Details

| SCOPE | 2026 turnaround mechanical decoke of the HDS Furnace naphtha passes, with filtration and smart-pig support |
| --- | --- |
| EXECUTION | September 25 – 27, 2026 (3 days) |
| HEATER | PR-175169 HDS Furnace |
| EQUIPMENT | (1) Trimax Pumper (Trimax 5) · (1) Support Unit · (1) Filter Press (Press 3) · Crew Truck |

Crew Details

| PROJECT MANAGER | Peter Campbell |
| --- | --- |
| SHIFT LEAD | Day — Peter Campbell; Night — James McDaniel |
| DAYSHIFT | Adrian Garza, David Charles, Marshall Douglas, Travis Trenholm |
| NIGHTSHIFT | Justin Kelly, Mikee Green, Jeremiah Harman |

Project Duration

| SCOPE | UNIT | RIG | PIG | SMART PIG | SUBTOTAL |
| --- | --- | --- | --- | --- | --- |
| PR-175169 HDS Furnace | Trimax 5 | 16 | 20.5 | 4.5 | 41 |

Stand-By Summary

Stand-by is on-site time during which the pumping units were not actively pigging. Cause is recorded from the daily service receipts.

| DATES | HOURS | CAUSE |
| --- | --- | --- |
| Sep 25 (8417) | 1 | Site safety review of hose routing near the catalyst job (HDS) |
| Sep 27 (8420) | 1 | Awaiting a 1600 CFM compressor to dewater (HDS) |
| TOTAL | 2 |  |

Heater total: 41 operating hours plus 2 stand-by hours — 43 pumping-unit hours.

PR-175169 — HDS Furnace

| Number of Passes | 4, looped into 2 circuits (passes 1 + 2, passes 3 + 4) |
| --- | --- |
| Total Footage | 3,600 ft (900 ft per pass) |
| Radiant Tube ID | 5.885" |
| Metallurgy | A335 P5 (radiant) |
| Smart Pigging | Yes |

Decoking Analysis:  Light fouling was found throughout the convection and radiant sections. Average pigging time was approximately 20.5 hours per circuit.

PR-175169 - task hours by shift, from the daily service receipts.

Pigs Used

| SIZE — QTY | SIZE — QTY |
| --- | --- |
| 6" — 4 | 6.25" — 12 |
| TOTAL — 16 |  |

Flow Tests

| Passes 1 + 2 (looped) GPM; BEFORE PSI; AFTER PSI; Δ PSI. 800; 320; 267; 53. 750; 290; 238; 52. 700; 250; 215; 35. | Passes 3 + 4 (looped) GPM; BEFORE PSI; AFTER PSI; Δ PSI. 650; 230; 180; 50. 600; 210; 170; 40. 550; 175; 140; 35. |
| --- | --- |

Project Summary

USADebusk performed the mechanical decoke of the HDS Furnace (PR-175169) for Cenovus at the Lima Refinery during the 2026 turnaround, September 25 – 27, on Trimax 5 with filtration through Press 3. The four naphtha passes were looped into two circuits, passes 1 + 2 and 3 + 4, and smart-pigged after cleaning. The heater ran 41 operating hours and 2 stand-by hours, using 16 pigs.

Project Close

The HDS Furnace was cleaned, rigged out and returned to Cenovus on September 27, 2026.

USADebusk thanks the Cenovus Lima team for their coordination and support throughout the turnaround, and we look forward to continuing to serve your decoking and pigging needs.

Peter Campbell  |  Pigging and Decoking SME

Cell: 832-920-4253  |  pcampbell@usadebusk.com