2026 TURNAROUND MECHANICAL DECOKE

Vacuum Charge Furnace — PR-170029

Job Report  |  USADebusk  |  Cenovus Lima Refinery — Lima, OH

| PROJECT NO. | FACILITY | EXECUTION | PROJECT MANAGER |
| --- | --- | --- | --- |
| USA26046 | Cenovus Lima Refinery | Sep 19 – 30, 2026 | Jesse Utsey |
| WORK ORDER | SCOPE | HEATER | DURATION |
| 82036776 | TA Mechanical Decoke | PR-170029 | 12 days |

| 195.5 | 52 | 97 | 8 |
| --- | --- | --- | --- |
| OPERATING HOURS | STAND-BY HOURS | PIGS RUN | PASSES |

Project Information

Customer Details

| FACILITY | Cenovus Lima Refinery |
| --- | --- |
| ADDRESS | 1150 S Metcalf St, Lima, OH 45804 |
| WORK ORDER | 82036776 |
| CONTACT | Alfredo Trevino |

Project Details

| SCOPE | 2026 turnaround mechanical decoke of the Vacuum Charge Furnace, with filtration and smart-pig support |
| --- | --- |
| EXECUTION | September 19 – 30, 2026 (12 days) |
| HEATER | PR-170029 Vacuum Charge Furnace |
| EQUIPMENT | (1) Trimax Pumper (Trimax 6) · (1) Support Unit · (1) Filter Press (Press 1) · Crew Truck |

Crew Details

| PROJECT MANAGER | Jesse Utsey |
| --- | --- |
| SHIFT LEAD | Day — Jesse Utsey; Night — Sam Mixon |
| DAYSHIFT | Danilo Ramirez, Blake Harman, Blake Baugh, Travis Trenholm, David Charles |
| NIGHTSHIFT | Tyler Garza, Joel Ruiz, Mikee Green |

Project Duration

| SCOPE | UNIT | RIG | PIG | SMART PIG | SUBTOTAL |
| --- | --- | --- | --- | --- | --- |
| PR-170029 Vacuum Charge Furnace | Trimax 6 | 58.5 | 63 | 74 | 195.5 |

Stand-By Summary

Stand-by is on-site time during which the pumping units were not actively pigging. Cause is recorded from the daily service receipts.

| DATES | HOURS | CAUSE |
| --- | --- | --- |
| Sep 19 – 21 (7077–7081) | 49 | Awaiting installation of the 12" radiant-outlet launchers (Vacuum) |
| Sep 26 (7091) | 3 | Awaiting relocation of the 12" launchers to passes 5, 7, 8 (Vacuum) |
| TOTAL | 52 |  |

Heater total: 195.5 operating hours plus 52 stand-by hours — 247.5 pumping-unit hours.

PR-170029 — Vacuum Charge Furnace

| Number of Passes | 8, pigged individually |
| --- | --- |
| Total Footage | 7,054 ft (882 ft per pass) |
| Convection Tube ID | 4.000" |
| Radiant Tube ID | 3.826" · 5.761" · 7.813" · 9.750" · 11.750" (4" to 12") |
| Metallurgy | A312 TP317/317L |
| Return Bends | 180° seamless |
| Smart Pigging | Yes — Intero |

Decoking Analysis:  Passes 4 and 5 carried the heaviest fouling, pass 5 the most. In pass 5, fouling was heavy in the 12" section, moderate in the 10" and 4" sections, and light in the 6" and 8" sections. In pass 4, it was moderate in the 12", light to moderate in the 10", and light in the 8", 6" and 4" sections. The remaining six passes showed light fouling throughout. The external 6" convection inlet piping, between the control valve and the 4" convection inlet tube, was heavily fouled on all eight passes, enough to keep 4" pigs from entering the convection section, and was cleaned first on each pass. Average pigging time was approximately 21 hours per pass.

PR-170029 - task hours by shift, from the daily service receipts.

Pigs Used

| SIZE — QTY | SIZE — QTY | SIZE — QTY | SIZE — QTY |
| --- | --- | --- | --- |
| 3.75" — 4 | 4.125" — 15 | 6.25" — 6 | 10" — 20 |
| 3.875" — 1 | 4.25" — 4 | 8" — 7 | 12" — 6 |
| 4" — 22 | 6" — 10 | 8.25" — 2 |  |
| TOTAL — 97 |  |  |  |

Flow Tests

| Pass 1 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 295; 220; 75. 650; 260; 185; 75. 600; 225; 165; 60. | Pass 2 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 275; 225; 50. 650; 235; 195; 40. 600; 205; 170; 35. |
| --- | --- |

| Pass 3 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 332; 282; 50. 650; 290; 250; 40. 600; 255; 220; 35. | Pass 4 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 280; 210; 70. 650; 235; 188; 47. 600; 210; 160; 50. |
| --- | --- |

| Pass 5 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 270; 220; 50. 650; 235; 190; 45. 600; 202; 160; 42. | Pass 6 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 285; 225; 60. 650; 235; 195; 40. 600; 210; 165; 45. |
| --- | --- |

| Pass 7 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 260; 220; 40. 650; 225; 185; 40. 600; 195; 160; 35. | Pass 8 GPM; BEFORE PSI; AFTER PSI; Δ PSI. 700; 320; 280; 40. 650; 280; 250; 30. 600; 240; 220; 20. |
| --- | --- |

Images

| Radiant outlet labels and orientation, viewed facing the outlets. Each outlet connects to the convection inlet of the same pass number. | Top: coke removed from the 12" tube, pass 5. Bottom: deposits removed from the external 6" convection inlet piping, collected from all eight passes. |
| --- | --- |

Project Summary

USADebusk performed the mechanical decoke of the Vacuum Charge Furnace (PR-170029) for Cenovus at the Lima Refinery during the 2026 turnaround, September 19 – 30, on Trimax 6 with filtration. The external 6" convection inlet piping was heavily fouled on all eight passes and was cleaned first on each pass, before pigging inside the heater. All eight passes were smart-pigged by Intero after cleaning. Of the heater's 247.5 pumping-unit hours, 52 were stand-by, waiting on the 12" radiant-outlet launchers to be installed and later relocated.

Project Close

The Vacuum Charge Furnace was cleaned and returned to Cenovus, and all equipment was demobilized from the unit on September 30, 2026.

USADebusk thanks the Cenovus Lima team for their coordination and support throughout the turnaround, and we look forward to continuing to serve your decoking and pigging needs.

Jesse Utsey  |  Project Manager, USADebusk

713-252-8516  |  JUtsey@USADebusk.com